## Implementation Matrix
Employee ID | Employee Name | Current Department | Final Department | Designation | Branch | Reporting Manager | ERP User Required | Existing ERP User Status | Primary Role | Secondary Role(s) | Authority Level | Branch Scope | Warehouse Scope | Approval Authority | Workspace Assignment | Implementation Phase | Action Required | Notes
HR-EMP-00001 | Kyaw Min Oo | Sales - MMOB | Executive Management | General Manager | Yangon | Managing Director | Yes | Review existing owner/admin mapping | General Manager | Sales/Purchase/Stock Manager; Branch Ops Reviewer; Pricing Reviewer | Manager | All Branches | All operating warehouses; restricted edit on control warehouses | Sales/Purchase/Inventory exceptions up to policy threshold | Executive / Operations | Phase A | Reassign department; create/link user; assign control roles | Acts as business head until formal COO/GM structure evolves
HR-EMP-00002 | Aung Ko Ko | Sales - MMOB | Sales and Channel Management | Sales Supervisor | Yangon | Kyaw Min Oo | Yes | Review possible mapping to sale.manager@meet.com | Sales Manager | Pricing Reviewer | Supervisor | Yangon primary; limited all-sales visibility | View stock in Yangon Main, Showroom, Mandalay | Routine sales approvals; discount review within threshold | Sales Manager | Phase A | Reassign department; confirm existing user mapping | Lead commercial approver below General Manager
HR-EMP-00003 | Htet Myat Aung | Sales - MMOB | Retail Sales | Sales Executive | Yangon | Aung Ko Ko | Yes | Review possible mapping to sale.user@meet.com | Sales User | - | Transaction User | Yangon | View Yangon Main and Showroom availability | None | Sales User | Phase A | Reassign department; confirm existing user mapping | Retail sales execution
HR-EMP-00004 | Nandar Oo | Sales - MMOB | Retail Sales | Sales Executive | Yangon | Aung Ko Ko | Yes | No | Sales User | - | Transaction User | Yangon | View Yangon Main and Showroom availability | None | Sales User | Phase B | Reassign department; create user | Retail sales execution
HR-EMP-00005 | Su Su Win | Sales - MMOB | Retail Sales | Sales Executive | Mandalay | Aung Ko Ko | Yes | No | Sales User | - | Transaction User | Mandalay | View Mandalay Warehouse availability | None | Sales User | Phase B | Reassign department; create user | Mandalay retail sales execution
HR-EMP-00006 | Tun Lin Oo | Sales - MMOB | Wholesale Sales | Key Account Sales | Mandalay | Aung Ko Ko | Yes | No | Sales User | Key Account / Wholesale coverage | Transaction User | Mandalay; assigned wholesale territories | View Mandalay Warehouse availability | None | Sales User | Phase B | Reassign department; create user | Key account and wholesale responsibility
HR-EMP-00007 | Zaw Lin | Warehouse - MMOB | Warehouse and Inventory | Warehouse Supervisor | Yangon | Kyaw Min Oo | Yes | No | Stock Manager | Delivery Manager; Inventory Controller | Supervisor | Yangon primary; cross-branch review for transfers | Yangon Main; Showroom support; Transit; Goods In Transit; view Mandalay | Routine stock approvals; transfer review; stock adjustment review | Warehouse Manager | Phase A | Reassign department; create user; assign control roles | Primary inventory control owner
HR-EMP-00008 | Soe Min Naing | Warehouse - MMOB | Inventory Control | Inventory Clerk | Yangon | Zaw Lin | Yes | No | Stock User | - | Transaction User | Yangon | Yangon Main; Transit support | None | Warehouse | Phase B | Reassign department; create user | Transaction and reconciliation support
HR-EMP-00009 | Ko Ko Naing | Warehouse - MMOB | Warehouse and Inventory | Storekeeper | Yangon | Zaw Lin | Yes | No | Stock User | Delivery User | Transaction User | Yangon | Yangon Main; Showroom if assigned | None | Warehouse | Phase B | Reassign department; create user | Picking, issue, transfer support
HR-EMP-00010 | Min Thu | Warehouse - MMOB | Warehouse and Inventory | Storekeeper | Mandalay | Zaw Lin | Yes | No | Stock User | Delivery User | Transaction User | Mandalay | Mandalay Warehouse; Transit support | None | Warehouse | Phase B | Reassign department; create user | Mandalay stock handling
HR-EMP-00011 | Hnin Pwint | Purchasing - MMOB | Procurement | Purchasing Officer | Yangon | Kyaw Min Oo | Yes | No | Purchase User | - | Transaction User | Yangon primary; supplier-wide | View Yangon Main and Transit needs | None | Procurement | Phase A | Reassign department; create user | Primary purchasing user for Yangon
HR-EMP-00012 | Thazin Myint | Purchasing - MMOB | Procurement | Purchasing Officer | Mandalay | Kyaw Min Oo | Yes | No | Purchase User | - | Transaction User | Mandalay primary; supplier-wide | View Mandalay stock needs | None | Procurement | Phase B | Reassign department; create user | Mandalay purchasing coordination
HR-EMP-00013 | Thandar Hlaing | Accounts - MMOB | Finance and Accounts | Accountant | Yangon | Finance Manager (acting) | Yes | No | Accounts User | - | Controller | All Branches | Financial only; warehouse view by report where needed | Routine accounting entries; no executive payment release | Finance | Phase A | Reassign department; create user; designate acting finance lead if selected | Strong candidate for acting Finance Lead
HR-EMP-00014 | May Nwe Thant | Accounts - MMOB | Finance and Accounts | Accountant | Mandalay | Finance Manager (acting) | Yes | No | Accounts User | - | Transaction User | Mandalay primary; cross-branch finance view as needed | Financial only | None | Finance | Phase B | Reassign department; create user | Mandalay finance operations
HR-EMP-00015 | May Thet Mon | Accounts - MMOB | Accounts Receivable | Cashier | Yangon | Finance Manager (acting) | Yes | No | Accounts User | Cash handling restriction | Restricted User | Yangon | Financial only | Cash receipts/payments within restricted workflow | Finance | Phase B | Reassign department; create user with restricted scope | Do not assign broad accounting permissions
HR-EMP-00016 | Ei Ei Phyo | HR and Admin - MMOB | HR and Admin | HR/Admin Officer | Yangon | Kyaw Min Oo | Yes | No | HR User | - | Restricted User | Yangon | None | Routine HR/Admin approvals only | Support | Phase C | Reassign department; create user | Employee records and admin processes
HR-EMP-00017 | Paing Htet Aung | IT - MMOB | ERP and IT | IT Support | Yangon | Kyaw Min Oo | Yes | Review existing technical/support access | Report Consumer | Potential future ERP Administrator | Support User | All Branches | None | None initially | Support | Phase C | Reassign department; create limited user; do not grant System Manager yet | Primary candidate for future ERP admin
HR-EMP-00018 | Pyae Sone Aung | IT - MMOB | ERP and IT | IT Support | Mandalay | Kyaw Min Oo | No | No | Report Consumer | - | No ERP User Initially | Mandalay | None | None | None | Phase C | Keep employee only; create user later if justified | Reserve for local support only
HR-EMP-00019 | Khin Sabai | Customer Service - MMOB | Customer Service | Customer Service Staff | Yangon | Kyaw Min Oo | Yes | No | Support Team | - | Restricted User | Yangon | View returns/service-related data only | None | Customer Service | Phase B | Reassign department; create user | After-sales and complaint handling
HR-EMP-00020 | Zin Min Htet | Customer Service - MMOB | Customer Service | Customer Service Staff | Mandalay | Kyaw Min Oo | Yes | No | Support Team | - | Restricted User | Mandalay | View returns/service-related data only | None | Customer Service | Phase B | Reassign department; create user | Mandalay service handling
HR-EMP-00021 | Ye Htut Naing | Delivery and Logistics - MMOB | Logistics and Distribution | Delivery Driver | Yangon | Zaw Lin | No | No | None initially | Potential Delivery User later | No ERP User Initially | Yangon | Operational through supervisor-controlled documents | None | None | Phase C | Keep employee only; evaluate mobile/limited access later | Delivery updates can remain supervisor-controlled initially
HR-EMP-00022 | Aye Chan Tun | Delivery and Logistics - MMOB | Logistics and Distribution | Delivery Driver | Mandalay | Zaw Lin | No | No | None initially | Potential Delivery User later | No ERP User Initially | Mandalay | Operational through supervisor-controlled documents | None | None | Phase C | Keep employee only; evaluate mobile/limited access later | Delivery updates can remain supervisor-controlled initially

## Summary
Implementation Summary
Metric | Value
Total Employees | 22
ERP Users Required | 18
No ERP User Initially | 4
Phase A Users | 6
Phase B Users | 11
Phase C Users | 5

## Legend
Field | Meaning
Final Department | Target standardized department after cleanup
Existing ERP User Status | Whether a current user appears to exist and needs review/mapping
Authority Level | Transaction User, Restricted User, Supervisor, Manager, Controller, Support User, or No ERP User Initially
Branch Scope | Business area in which the user should operate
Warehouse Scope | Warehouses the user may transact in or review
Approval Authority | Target workflow authority level
Implementation Phase | Suggested rollout sequence: Phase A key control users, Phase B operational users, Phase C support/optional users