## Overview
Mingalar ERP Development-Stage Role-Slot Implementation Pack
Purpose | Configuration-ready pack for development-stage placeholder accounts, DocType permissions, and workflow routing.
Design Rule | Use role-slot accounts during design/development. Replace with personal named users before go-live.
Business Footprint Preserved | 1 company, 2 branches, 10 warehouses, 65 customers, 57 items, 7 suppliers.
Approval Rule | Cross-functional approvals route to GM. Finance-only approvals route to Finance Lead.
Acting Finance Lead | finance.lead@meet.com is assigned temporarily to the Yangon lead accountant seat until a formal Finance Manager seat is created.
Initial ERP Seat Plan | 18 initial ERP seats; delivery drivers remain employee-only in Phase 1; one Mandalay IT support seat deferred.
Workbook Structure | Overview, Role-Slot Plan, DocType Permissions, Workflow Spec.
Implementation Notes
1 | Placeholder accounts are designed as role slots rather than shared generic logins. Example: sales.exec.ygn.01@meet.com.
2 | Role-slot accounts should map one-to-one to an intended operating seat. Avoid one generic sales.user account covering multiple people.
3 | Before production, disable placeholder business accounts and create personal named users with the same role/profile/permission design.
4 | Returns/Damaged and Transit warehouses remain restricted-control locations and are not broadly editable by all stock users.

## Role-Slot Plan
Development-Stage Placeholder Role-Slot User Plan
Slot Email | Seat Type | Current/Future Owner | Branch | Current Department | Target Department | Designation/Seat | ERP User in Dev? | Go-Live Personal User? | Primary Role Profile | Secondary Roles | Authority Level | Branch Scope | Warehouse Scope | Workspace | Action Required
gm@meet.com | Current employee-backed | Kyaw Min Oo | Yangon | Sales - MMOB | Executive Management | General Manager | Yes | Replace with personal user before go-live | General Manager | Sales Manager; Purchase Manager; Stock Manager; Branch Operations Reviewer | Manager / Cross-functional approver | All branches | All warehouses (review); no routine stock posting | Executive Workspace | Create in Phase A
finance.lead@meet.com | Current employee-backed | Thandar Hlaing (acting lead) | Yangon | Accounts - MMOB | Finance and Accounts | Acting Finance Lead | Yes | Replace with personal user before go-live | Finance Lead | Accounts Manager; Payment Reviewer; Credit Control Reviewer | Manager / Finance approver | All branches | Finance review only; no warehouse transaction ownership | Finance Workspace | Create in Phase A
sales.supervisor@meet.com | Current employee-backed | Aung Ko Ko | Yangon | Sales - MMOB | Sales and Channel Management | Sales Supervisor | Yes | Replace with personal user before go-live | Sales Supervisor | Sales Manager; Pricing Reviewer | Supervisor / Routine sales approver | All branches (sales review); own team execution | View all saleable warehouses | Sales Workspace | Create in Phase A
sales.exec.ygn.01@meet.com | Current employee-backed | Htet Myat Aung | Yangon | Sales - MMOB | Retail Sales | Sales Executive | Yes | Replace with personal user before go-live | Retail Sales Executive | Sales User | Transaction user | Yangon | View Yangon Main + Showroom stock only | Sales Workspace | Create in Phase A
sales.exec.ygn.02@meet.com | Current employee-backed | Nandar Oo | Yangon | Sales - MMOB | Retail Sales | Sales Executive | Yes | Replace with personal user before go-live | Retail Sales Executive | Sales User | Transaction user | Yangon | View Yangon Main + Showroom stock only | Sales Workspace | Create in Phase B
sales.exec.mdy.01@meet.com | Current employee-backed | Su Su Win | Mandalay | Sales - MMOB | Retail Sales | Sales Executive | Yes | Replace with personal user before go-live | Retail Sales Executive | Sales User | Transaction user | Mandalay | View Mandalay Warehouse stock only | Sales Workspace | Create in Phase B
keyaccount.mdy.01@meet.com | Current employee-backed | Tun Lin Oo | Mandalay | Sales - MMOB | Wholesale Sales | Key Account Sales | Yes | Replace with personal user before go-live | Wholesale / Key Account Executive | Sales User | Transaction user | Mandalay + assigned external territories | View saleable stock across Yangon/Mandalay | Sales Workspace | Create in Phase B
warehouse.supervisor.ygn@meet.com | Current employee-backed | Zaw Lin | Yangon | Warehouse - MMOB | Warehouse and Inventory | Warehouse Supervisor | Yes | Replace with personal user before go-live | Warehouse Supervisor | Stock Manager; Delivery Manager; Inventory Controller | Supervisor / Inventory approver | Yangon primary; review Mandalay if needed | Yangon Main; Showroom; Transit; Returns review | Warehouse Workspace | Create in Phase A
inventory.ygn.01@meet.com | Current employee-backed | Soe Min Naing | Yangon | Warehouse - MMOB | Inventory Control | Inventory Clerk | Yes | Replace with personal user before go-live | Inventory Clerk | Stock User | Transaction user | Yangon | Yangon Main; Transit (restricted ops) | Warehouse Workspace | Create in Phase B
storekeeper.ygn.01@meet.com | Current employee-backed | Ko Ko Naing | Yangon | Warehouse - MMOB | Warehouse and Inventory | Storekeeper | Yes | Replace with personal user before go-live | Storekeeper | Stock User; Delivery User | Transaction user | Yangon | Yangon Main; Showroom dispatch only if assigned | Warehouse Workspace | Create in Phase B
storekeeper.mdy.01@meet.com | Current employee-backed | Min Thu | Mandalay | Warehouse - MMOB | Warehouse and Inventory | Storekeeper | Yes | Replace with personal user before go-live | Storekeeper | Stock User; Delivery User | Transaction user | Mandalay | Mandalay Warehouse only | Warehouse Workspace | Create in Phase B
purchase.ygn.01@meet.com | Current employee-backed | Hnin Pwint | Yangon | Purchasing - MMOB | Procurement | Purchasing Officer | Yes | Replace with personal user before go-live | Purchase Officer | Purchase User | Transaction user | Yangon | No warehouse posting; view inbound destinations | Procurement Workspace | Create in Phase A
purchase.mdy.01@meet.com | Current employee-backed | Thazin Myint | Mandalay | Purchasing - MMOB | Procurement | Purchasing Officer | Yes | Replace with personal user before go-live | Purchase Officer | Purchase User | Transaction user | Mandalay | No warehouse posting; view inbound destinations | Procurement Workspace | Create in Phase B
accounts.ygn.01@meet.com | Current employee-backed | Thandar Hlaing | Yangon | Accounts - MMOB | Accounts Receivable / Payable | Accountant | Yes | Replace with personal user before go-live | Accountant | Accounts User | Transaction user | All branches (finance) | No warehouse posting | Finance Workspace | Create in Phase A; dual hat with acting finance lead in design stage
accounts.mdy.01@meet.com | Current employee-backed | May Nwe Thant | Mandalay | Accounts - MMOB | Accounts Receivable / Payable | Accountant | Yes | Replace with personal user before go-live | Accountant | Accounts User | Transaction user | All branches (finance) | No warehouse posting | Finance Workspace | Create in Phase B
cashier.ygn.01@meet.com | Current employee-backed | May Thet Mon | Yangon | Accounts - MMOB | Finance and Accounts | Cashier | Yes | Replace with personal user before go-live | Cashier | Accounts User | Restricted transaction user | Yangon | No warehouse posting | Finance Workspace | Create in Phase B
hr.admin.ygn@meet.com | Current employee-backed | Ei Ei Phyo | Yangon | HR and Admin - MMOB | HR and Admin | HR/Admin Officer | Yes | Replace with personal user before go-live | HR/Admin Officer | HR User | Restricted functional user | Yangon primary | No warehouse scope | Support Workspace | Create in Phase C
cs.ygn.01@meet.com | Current employee-backed | Khin Sabai | Yangon | Customer Service - MMOB | Customer Service | Customer Service Staff | Yes | Replace with personal user before go-live | Customer Service User | Support Team | Restricted functional user | Yangon | View Returns/Damaged only as inquiry if needed | Customer Service Workspace | Create in Phase B
cs.mdy.01@meet.com | Current employee-backed | Zin Min Htet | Mandalay | Customer Service - MMOB | Customer Service | Customer Service Staff | Yes | Replace with personal user before go-live | Customer Service User | Support Team | Restricted functional user | Mandalay | View Returns/Damaged only as inquiry if needed | Customer Service Workspace | Create in Phase B
it.ygn.01@meet.com | Current employee-backed | Paing Htet Aung | Yangon | IT - MMOB | ERP and IT | IT Support | Yes | Replace with personal user before go-live | IT Support | Report Consumer | Support user | All branches (support) | No warehouse transaction scope | Support Workspace | Create in Phase C
it.mdy.01@meet.com | Current employee-backed | Pyae Sone Aung | Mandalay | IT - MMOB | ERP and IT | IT Support | No - defer | Replace with personal user only if needed later | IT Support | Report Consumer | Support user | Mandalay | No warehouse transaction scope | Support Workspace | Defer / phase later
delivery.ygn.01@meet.com | Current employee-backed | Ye Htut Naing | Yangon | Delivery and Logistics - MMOB | Logistics and Distribution | Delivery Driver | No - employee only | Not planned unless later required | Delivery Driver | None | No ERP seat in Phase 1 | Yangon | N/A | N/A | Keep employee only for now
delivery.mdy.01@meet.com | Current employee-backed | Aye Chan Tun | Mandalay | Delivery and Logistics - MMOB | Logistics and Distribution | Delivery Driver | No - employee only | Not planned unless later required | Delivery Driver | None | No ERP seat in Phase 1 | Mandalay | N/A | N/A | Keep employee only for now
md.approver@meet.com | Planned governance seat | Future Managing Director seat | Corporate | (planned) | Executive Management | Managing Director | Optional later | Use personal named executive account before go-live | Managing Director | Executive Approver; Report Consumer | Executive approver | All branches | All warehouses (review only) | Executive Workspace | Planned future seat; not required for first build
erp.admin@meet.com | Planned governance seat | Future ERP Admin seat | Corporate | (planned) | ERP and IT | ERP Administrator | Optional later | Use personal named admin account before go-live | ERP Administrator | Workspace Manager; Report Manager | System authority | All branches | No business transaction ownership | Support Workspace | Planned future seat; introduce only when governance matures
Note on A4: Development-stage role-slot account. Replace with a personal named executive user before production.

## DocType Permissions
DocType Permission Matrix by Role Profile / Role Slot Group
Role Profile | Representative Slot(s) | DocType | Read | Create | Edit | Submit | Approve | Cancel | Scope Rule | Approval Note | Primary Workspace | Implementation Phase
General Manager | gm@meet.com | Quotation | Yes | No | No | Review only | Yes | No | All branches, management review only | Cross-functional approvals and escalations | Executive Workspace | A
General Manager | gm@meet.com | Sales Order | Yes | No | No | Review only | Yes | No | All branches, management review only | Cross-functional approvals and escalations | Executive Workspace | A
General Manager | gm@meet.com | Purchase Order | Yes | No | No | Review only | Yes | No | All branches, management review only | Cross-functional approvals and escalations | Executive Workspace | A
General Manager | gm@meet.com | Stock Entry | Yes | No | No | Review only | No | No | All branches, management review only | Cross-functional approvals and escalations | Executive Workspace | A
General Manager | gm@meet.com | Stock Reconciliation | Yes | No | No | Review only | No | No | All branches, management review only | Cross-functional approvals and escalations | Executive Workspace | A
General Manager | gm@meet.com | Payment Entry | Yes | No | No | Review only | No | No | All branches, management review only | Cross-functional approvals and escalations | Executive Workspace | A
General Manager | gm@meet.com | Sales Invoice | Yes | No | No | Review only | No | No | All branches, management review only | Cross-functional approvals and escalations | Executive Workspace | A
General Manager | gm@meet.com | Purchase Invoice | Yes | No | No | Review only | No | No | All branches, management review only | Cross-functional approvals and escalations | Executive Workspace | A
General Manager | gm@meet.com | Workflow / Exception Review | Yes | No | No | Review only | Yes | No | All branches, management review only | Cross-functional approvals and escalations | Executive Workspace | A
Finance Lead | finance.lead@meet.com | Sales Order | Yes | No | Review only | Review only | No | No | All branches, finance control only | Finance approvals and credit/risk review | Finance Workspace | A
Finance Lead | finance.lead@meet.com | Sales Invoice | Yes | No | Review only | Yes | No | No | All branches, finance control only | Finance approvals and credit/risk review | Finance Workspace | A
Finance Lead | finance.lead@meet.com | Purchase Invoice | Yes | No | Review only | Yes | No | No | All branches, finance control only | Finance approvals and credit/risk review | Finance Workspace | A
Finance Lead | finance.lead@meet.com | Payment Entry | Yes | No | Review only | Yes | Yes | No | All branches, finance control only | Finance approvals and credit/risk review | Finance Workspace | A
Finance Lead | finance.lead@meet.com | Journal Entry | Yes | No | Review only | Yes | No | No | All branches, finance control only | Finance approvals and credit/risk review | Finance Workspace | A
Finance Lead | finance.lead@meet.com | Stock Reconciliation | Yes | No | Review only | Review only | No | No | All branches, finance control only | Finance approvals and credit/risk review | Finance Workspace | A
Sales Supervisor | sales.supervisor@meet.com | Lead | Yes | Yes | Yes | No | No | No | All sales branches; team and customer review | Routine sales approval; pricing review | Sales Workspace | A
Sales Supervisor | sales.supervisor@meet.com | Opportunity | Yes | Yes | Yes | No | No | No | All sales branches; team and customer review | Routine sales approval; pricing review | Sales Workspace | A
Sales Supervisor | sales.supervisor@meet.com | Quotation | Yes | No | Yes | Yes | Yes | No | All sales branches; team and customer review | Routine sales approval; pricing review | Sales Workspace | A
Sales Supervisor | sales.supervisor@meet.com | Sales Order | Yes | No | Yes | Yes | Yes | No | All sales branches; team and customer review | Routine sales approval; pricing review | Sales Workspace | A
Sales Supervisor | sales.supervisor@meet.com | Customer | Yes | No | Yes | No | No | No | All sales branches; team and customer review | Routine sales approval; pricing review | Sales Workspace | A
Retail Sales Executive | sales.exec.* | Lead | Yes | Yes | Yes | No | No | No | Assigned branch, assigned customers, read-only stock visibility | No approval authority | Sales Workspace | A/B
Retail Sales Executive | sales.exec.* | Opportunity | Yes | Yes | Yes | No | No | No | Assigned branch, assigned customers, read-only stock visibility | No approval authority | Sales Workspace | A/B
Retail Sales Executive | sales.exec.* | Quotation | Yes | Yes | Yes | No | No | No | Assigned branch, assigned customers, read-only stock visibility | No approval authority | Sales Workspace | A/B
Retail Sales Executive | sales.exec.* | Sales Order | Yes | Yes | Yes | No | No | No | Assigned branch, assigned customers, read-only stock visibility | No approval authority | Sales Workspace | A/B
Retail Sales Executive | sales.exec.* | Customer | Yes | No | No | No | No | No | Assigned branch, assigned customers, read-only stock visibility | No approval authority | Sales Workspace | A/B
Retail Sales Executive | sales.exec.* | Item | Yes | No | No | No | No | No | Assigned branch, assigned customers, read-only stock visibility | No approval authority | Sales Workspace | A/B
Wholesale / Key Account Executive | keyaccount.mdy.01@meet.com | Lead | Yes | Yes | Yes | No | No | No | Assigned territories and wholesale customers; cross-branch stock visibility | No approval authority | Sales Workspace | B
Wholesale / Key Account Executive | keyaccount.mdy.01@meet.com | Opportunity | Yes | Yes | Yes | No | No | No | Assigned territories and wholesale customers; cross-branch stock visibility | No approval authority | Sales Workspace | B
Wholesale / Key Account Executive | keyaccount.mdy.01@meet.com | Quotation | Yes | Yes | Yes | No | No | No | Assigned territories and wholesale customers; cross-branch stock visibility | No approval authority | Sales Workspace | B
Wholesale / Key Account Executive | keyaccount.mdy.01@meet.com | Sales Order | Yes | Yes | Yes | No | No | No | Assigned territories and wholesale customers; cross-branch stock visibility | No approval authority | Sales Workspace | B
Wholesale / Key Account Executive | keyaccount.mdy.01@meet.com | Customer | Yes | No | No | No | No | No | Assigned territories and wholesale customers; cross-branch stock visibility | No approval authority | Sales Workspace | B
Wholesale / Key Account Executive | keyaccount.mdy.01@meet.com | Item | Yes | No | No | No | No | No | Assigned territories and wholesale customers; cross-branch stock visibility | No approval authority | Sales Workspace | B
Purchase Officer | purchase.* | Supplier Quotation | Yes | Yes | Yes | No | No | No | Assigned branch procurement scope; no payment release | Purchase creation only | Procurement Workspace | A/B
Purchase Officer | purchase.* | Request for Quotation | Yes | Yes | Yes | No | No | No | Assigned branch procurement scope; no payment release | Purchase creation only | Procurement Workspace | A/B
Purchase Officer | purchase.* | Purchase Order | Yes | Yes | Yes | No | No | No | Assigned branch procurement scope; no payment release | Purchase creation only | Procurement Workspace | A/B
Purchase Officer | purchase.* | Material Request | Yes | No | No | No | No | No | Assigned branch procurement scope; no payment release | Purchase creation only | Procurement Workspace | A/B
Purchase Officer | purchase.* | Supplier | Yes | No | No | No | No | No | Assigned branch procurement scope; no payment release | Purchase creation only | Procurement Workspace | A/B
Purchase Officer | purchase.* | Item | Yes | No | No | No | No | No | Assigned branch procurement scope; no payment release | Purchase creation only | Procurement Workspace | A/B
Warehouse Supervisor | warehouse.supervisor.ygn@meet.com | Purchase Receipt | Yes | No | Yes | Yes | No | No | Assigned warehouses plus controlled review of transit/returns | Inventory movement approval; discrepancy escalation | Warehouse Workspace | A
Warehouse Supervisor | warehouse.supervisor.ygn@meet.com | Delivery Note | Yes | No | Yes | Yes | No | No | Assigned warehouses plus controlled review of transit/returns | Inventory movement approval; discrepancy escalation | Warehouse Workspace | A
Warehouse Supervisor | warehouse.supervisor.ygn@meet.com | Stock Entry | Yes | Yes | Yes | Yes | Yes | No | Assigned warehouses plus controlled review of transit/returns | Inventory movement approval; discrepancy escalation | Warehouse Workspace | A
Warehouse Supervisor | warehouse.supervisor.ygn@meet.com | Stock Reconciliation | Yes | Yes | Yes | Review only | Yes | No | Assigned warehouses plus controlled review of transit/returns | Inventory movement approval; discrepancy escalation | Warehouse Workspace | A
Warehouse Supervisor | warehouse.supervisor.ygn@meet.com | Pick List | Yes | Yes | Yes | Review only | No | No | Assigned warehouses plus controlled review of transit/returns | Inventory movement approval; discrepancy escalation | Warehouse Workspace | A
Warehouse Supervisor | warehouse.supervisor.ygn@meet.com | Warehouse | Yes | No | Yes | Review only | No | No | Assigned warehouses plus controlled review of transit/returns | Inventory movement approval; discrepancy escalation | Warehouse Workspace | A
Warehouse Supervisor | warehouse.supervisor.ygn@meet.com | Item | Yes | No | Yes | Review only | No | No | Assigned warehouses plus controlled review of transit/returns | Inventory movement approval; discrepancy escalation | Warehouse Workspace | A
Inventory / Storekeeper | inventory.ygn.01@meet.com; storekeeper.* | Purchase Receipt | Yes | Yes | Yes | Yes | No | No | Assigned operating warehouse only | No approval authority | Warehouse Workspace | B
Inventory / Storekeeper | inventory.ygn.01@meet.com; storekeeper.* | Delivery Note | Yes | Yes | Yes | Yes | No | No | Assigned operating warehouse only | No approval authority | Warehouse Workspace | B
Inventory / Storekeeper | inventory.ygn.01@meet.com; storekeeper.* | Stock Entry | Yes | Yes | Yes | Yes | No | No | Assigned operating warehouse only | No approval authority | Warehouse Workspace | B
Inventory / Storekeeper | inventory.ygn.01@meet.com; storekeeper.* | Pick List | Yes | Yes | Yes | No | No | No | Assigned operating warehouse only | No approval authority | Warehouse Workspace | B
Inventory / Storekeeper | inventory.ygn.01@meet.com; storekeeper.* | Warehouse | Yes | No | No | No | No | No | Assigned operating warehouse only | No approval authority | Warehouse Workspace | B
Inventory / Storekeeper | inventory.ygn.01@meet.com; storekeeper.* | Item | Yes | No | No | No | No | No | Assigned operating warehouse only | No approval authority | Warehouse Workspace | B
Accountant | accounts.* | Sales Invoice | Yes | Yes | Yes | Yes | No | No | All branches, finance scope only | No executive approvals | Finance Workspace | A/B
Accountant | accounts.* | Purchase Invoice | Yes | Yes | Yes | Yes | No | No | All branches, finance scope only | No executive approvals | Finance Workspace | A/B
Accountant | accounts.* | Payment Entry | Yes | Yes | Yes | Yes | No | No | All branches, finance scope only | No executive approvals | Finance Workspace | A/B
Accountant | accounts.* | Journal Entry | Yes | Yes | Yes | Yes | No | No | All branches, finance scope only | No executive approvals | Finance Workspace | A/B
Accountant | accounts.* | Customer | Yes | No | No | No | No | No | All branches, finance scope only | No executive approvals | Finance Workspace | A/B
Accountant | accounts.* | Supplier | Yes | No | No | No | No | No | All branches, finance scope only | No executive approvals | Finance Workspace | A/B
Cashier | cashier.ygn.01@meet.com | Payment Entry | Yes | Yes | Yes | No | No | No | Cash desk transactions only | No approval authority | Finance Workspace | B
Cashier | cashier.ygn.01@meet.com | Sales Invoice | Yes | No | No | No | No | No | Cash desk transactions only | No approval authority | Finance Workspace | B
Cashier | cashier.ygn.01@meet.com | Customer | Yes | No | No | No | No | No | Cash desk transactions only | No approval authority | Finance Workspace | B
HR/Admin Officer | hr.admin.ygn@meet.com | Employee | Yes | Yes | Yes | No | No | No | HR/admin scope only | No business approval authority outside HR/admin | Support Workspace | C
HR/Admin Officer | hr.admin.ygn@meet.com | Leave Application | Yes | Yes | Yes | Yes | No | No | HR/admin scope only | No business approval authority outside HR/admin | Support Workspace | C
HR/Admin Officer | hr.admin.ygn@meet.com | Expense Claim | Yes | Yes | Yes | No | No | No | HR/admin scope only | No business approval authority outside HR/admin | Support Workspace | C
Customer Service User | cs.* | Issue | Yes | Yes | Yes | No | No | No | Assigned branch service cases; inquiry access to customer history | No approval authority | Customer Service Workspace | B
Customer Service User | cs.* | Customer | Yes | No | No | No | No | No | Assigned branch service cases; inquiry access to customer history | No approval authority | Customer Service Workspace | B
Customer Service User | cs.* | Delivery Note | Yes | No | No | No | No | No | Assigned branch service cases; inquiry access to customer history | No approval authority | Customer Service Workspace | B
Customer Service User | cs.* | Sales Invoice | Yes | No | No | No | No | No | Assigned branch service cases; inquiry access to customer history | No approval authority | Customer Service Workspace | B
IT Support | it.* | Prepared Report | Yes | No | No | No | No | No | Support monitoring only | No business transaction rights | Support Workspace | C
IT Support | it.* | Error Log | Yes | No | No | No | No | No | Support monitoring only | No business transaction rights | Support Workspace | C
IT Support | it.* | Scheduled Job Log | Yes | No | No | No | No | No | Support monitoring only | No business transaction rights | Support Workspace | C
Managing Director | md.approver@meet.com | Executive Approval Queue | Yes | No | No | Review only | Yes | No | All branches, review only | Final exceptional approvals only | Executive Workspace | Future
Managing Director | md.approver@meet.com | Quotation | Yes | No | No | Review only | Yes | No | All branches, review only | Final exceptional approvals only | Executive Workspace | Future
Managing Director | md.approver@meet.com | Purchase Order | Yes | No | No | Review only | Yes | No | All branches, review only | Final exceptional approvals only | Executive Workspace | Future
Managing Director | md.approver@meet.com | Payment Entry | Yes | No | No | Review only | Yes | No | All branches, review only | Final exceptional approvals only | Executive Workspace | Future
ERP Administrator | erp.admin@meet.com | User | Yes | Yes | Yes | N/A | N/A | N/A | System administration only | Not a business approver | Support Workspace | Future
ERP Administrator | erp.admin@meet.com | Role | Yes | Yes | Yes | N/A | N/A | N/A | System administration only | Not a business approver | Support Workspace | Future
ERP Administrator | erp.admin@meet.com | Workspace | Yes | Yes | Yes | N/A | N/A | N/A | System administration only | Not a business approver | Support Workspace | Future
ERP Administrator | erp.admin@meet.com | Workflow | Yes | Yes | Yes | N/A | N/A | N/A | System administration only | Not a business approver | Support Workspace | Future
ERP Administrator | erp.admin@meet.com | Report | Yes | Yes | Yes | N/A | N/A | N/A | System administration only | Not a business approver | Support Workspace | Future
Note on C4: Representative DocTypes selected for the first implementation wave. Expand later if additional modules are introduced.

## Workflow Spec
Development-Stage Workflow Specification
Process | DocType | Step No. | From Role | Action | To Role | Trigger / Threshold | System Outcome | Primary Queue / Workspace | Phase | Notes
Sales Approval | Quotation | 1 | Retail/Wholesale Sales Executive | Create Draft | Sales Supervisor | Routine quotation | Draft quotation created | Sales Workspace | A/B | Sales user prepares commercial proposal
Sales Approval | Quotation | 2 | Sales Supervisor | Approve / Return | General Manager | Only if discount exception, unusual terms, or margin concern | Approved or escalated quotation | Sales Workspace | A | GM handles cross-functional commercial judgment
Sales Approval | Sales Order | 1 | Retail/Wholesale Sales Executive | Create Draft | Sales Supervisor | Routine sales order | Draft sales order created | Sales Workspace | A/B | Customer, item, quantity, warehouse confirmed
Sales Approval | Sales Order | 2 | Sales Supervisor | Approve / Escalate | Finance Lead | Only if credit-risk or receivable concern | Order approved or escalated to finance | Sales Workspace | A | Finance only joins when financial exposure exists
Sales Approval | Sales Order | 3 | Finance Lead | Approve / Hold | General Manager | Only if cross-functional or exceptional case remains | Order approved, held, or escalated | Finance Workspace | A | GM resolves cross-functional conflicts
Procurement Approval | Purchase Order | 1 | Purchase Officer | Create Draft | General Manager | Routine purchasing | Draft PO created | Procurement Workspace | A/B | Officer prepares PO based on replenishment need
Procurement Approval | Purchase Order | 2 | General Manager | Approve / Escalate | Finance Lead | Higher value, cash-sensitive, or unusual procurement | PO approved or escalated | Executive Workspace | A | GM owns routine cross-functional commercial decision
Procurement Approval | Purchase Order | 3 | Finance Lead | Approve / Escalate | Managing Director | Only if exceptional financial commitment | PO approved or escalated | Finance Workspace | Future | MD seat optional later
Inventory Control | Stock Entry | 1 | Inventory Clerk / Storekeeper | Create Draft | Warehouse Supervisor | Routine transfer / issue / receipt-related stock movement | Draft stock movement created | Warehouse Workspace | B | Restricted to assigned warehouses
Inventory Control | Stock Entry | 2 | Warehouse Supervisor | Submit / Escalate | Finance Lead | If adjustment or valuation-sensitive movement | Stock entry submitted or escalated | Warehouse Workspace | A | Supervisor handles normal operational control
Inventory Control | Stock Reconciliation | 1 | Warehouse Supervisor | Create Draft | Finance Lead | Discrepancy, count variance, damaged stock impact | Draft reconciliation created | Warehouse Workspace | A | Reconciliation is control-sensitive
Inventory Control | Stock Reconciliation | 2 | Finance Lead | Approve / Escalate | General Manager | If loss/valuation is material or cross-functional | Reconciliation approved or escalated | Finance Workspace | A | GM handles major operational-financial exceptions
Finance Control | Payment Entry | 1 | Accountant / Cashier | Prepare Payment | Finance Lead | Routine supplier payment or receipt settlement | Payment prepared and routed | Finance Workspace | A/B | Cashier remains restricted user
Finance Control | Payment Entry | 2 | Finance Lead | Approve / Escalate | Managing Director | Only if exceptional amount or unusual financial release | Payment approved or escalated | Finance Workspace | A/Future | MD only for exceptional releases
Note on A4: Workflow design uses GM for cross-functional approvals and Finance Lead for finance-only approvals, per approved policy.