## Overview
Mingalar ERP Workspace Configuration Matrix
Document Purpose | Translate the approved role-based workspace blueprint into a configuration-ready matrix for ERPNext setup.
Current Stage | Foundation and workflow layers are already implemented. The next user-facing phase is role-based workspace and navigation refinement.
Implementation Principle | Start with first-wave workspaces for daily operations, then add second-wave management and support workspaces.
First-Wave Workspaces | Sales Console; Procurement Console; Warehouse Console; Finance Console
Second-Wave Workspaces | Executive Console; Customer Service Console; HR and Admin Console; ERP Admin Console
Design Rule | Each workspace should show only the transactions, approvals, and reports most relevant to the role family.
Next Use | This workbook should be used as the reference for actual workspace creation, shortcut selection, report placement, and role assignment.
Recommended Delivery Order
1. Create Sales Console
2. Create Procurement Console
3. Create Warehouse Console
4. Create Finance Console
5. Validate with role-slot users
6. Create Executive Console
7. Create Customer Service / HR / ERP Admin consoles

## Workspace Matrix
Wave | Workspace Name | Target Users / Roles | Primary Purpose | Primary Shortcuts | Primary Reports | Approval / Review Links | Visibility Model | Rollout Priority | Notes
First Wave | Sales Console | Sales Supervisor; Sales Executives; Key Account Sales | Daily customer-facing selling, quotation/order entry, customer follow-up | Opportunity; Quotation; Sales Order; Customer; Item | Sales Analytics; Item-wise Sales Register; Customer-wise Sales History; Open Orders | Quotations pending approval; escalated quotations; open sales orders | Restricted to sales role family | 1 | Primary entry point for all sales users; should replace day-to-day reliance on generic Selling workspace
First Wave | Procurement Console | Purchase Officers; GM for review | Supplier coordination, RFQ / supplier quotation / purchase order handling, replenishment review | Request for Quotation; Supplier Quotation; Purchase Order; Supplier; Item | Purchase Analytics; Supplier-wise Purchase Register; Ordered Items To Be Delivered | Purchase orders pending approval; supplier comparison review | Restricted to procurement role family | 2 | Should highlight purchasing workflow state and expected arrival visibility
First Wave | Warehouse Console | Warehouse Supervisor; Inventory Clerk; Storekeepers | Stock movement, receiving, transfer, dispatch, and warehouse control | Stock Entry; Warehouse; Item; Stock Balance; Stock Ledger | Stock Balance; Stock Ledger; Item Balance; Movement / transfer review | Stock entries pending approval; transit / returns visibility for authorized users | Restricted to warehouse role family | 3 | Queue-based layout recommended; minimal cross-module clutter
First Wave | Finance Console | Finance Lead; Accountants; Cashier | Receivables, payables, invoicing, payment preparation, financial review | Payment Entry; Sales Invoice; Purchase Invoice; Journal Entry; Customer; Supplier | Accounts Receivable Summary; Accounts Payable Summary; General Ledger; Cash / bank reviews | Payments pending approval; journal review; receivable exposure | Restricted to finance role family | 4 | Finance users should not need to navigate through stock or CRM workspaces for routine work
Second Wave | Executive Console | Managing Director; General Manager; Finance Lead for cross-functional visibility | Management dashboard, exception review, branch comparison, approval oversight | Quotation; Purchase Order; Stock Entry; Payment Entry; Customer; Item | Sales Analytics; Accounts Receivable Summary; Stock Balance; management KPI reports | Major approvals; cross-functional exceptions; workflow backlog review | Restricted to executive / oversight users | 5 | Should be report-first, not transaction-first
Second Wave | Customer Service Console | Customer Service Staff | Customer issue handling, return follow-up, service case review | Issue; Customer; Item; return/service links | Issue summary; open case aging; return/service backlog | Open issues; unresolved customer cases; return-related review links | Restricted to service role family | 6 | Should expose only customer and service-relevant items
Second Wave | HR and Admin Console | HR/Admin Officer | Employee, leave, attendance, and basic administrative management | Employee; Leave Application; Attendance; Department; Designation | Employee list; leave status; attendance summary | Approval links for HR/admin items only if later needed | Restricted to HR/Admin users | 7 | Should remain isolated from commercial and stock-heavy workspaces
Second Wave | ERP Admin Console | IT Support; future ERP Administrator | Controlled setup, governance, user, permission, and workflow maintenance | User; Role; User Permission; Workflow; Workspace; Department; Designation | User access review; workflow review; setup review | Setup review; governance maintenance; configuration monitoring | Restricted to ERP admin / support users | 8 | Not intended for ordinary business users

## Navigation Rules
Role Family | Primary Workspace | Should Avoid as Daily Entry Point | Navigation Intent
Executive / Management | Executive Console | Selling; Buying; Stock; generic transaction workspaces | Use reports, approvals, and exception visibility first
Sales | Sales Console | Buying; Stock; HR; ERP settings | Stay customer- and quotation-focused
Procurement | Procurement Console | CRM; Payroll; broad stock workspaces | Stay supplier- and purchasing-focused
Warehouse / Inventory | Warehouse Console | CRM; HR; Finance-heavy workspaces | Stay movement- and stock-focused
Finance | Finance Console | CRM; Warehouse movement workspaces | Stay party balance and payment focused
Customer Service | Customer Service Console | Buying; Payroll; broad finance screens | Stay issue- and return-focused
HR/Admin | HR and Admin Console | Selling; Buying; Stock | Stay employee- and attendance-focused
ERP Admin / IT | ERP Admin Console | Operational consoles unless troubleshooting | Stay governance- and setup-focused

## Form Priorities
DocType | Primary Role Family | Fields / Sections to Surface First | Fields / Sections to Collapse or De-emphasize
Quotation | Sales | Customer; items; quantity; rate; delivery date; workflow state | advanced accounting fields; internal technical sections
Sales Order | Sales | Customer; items; quantity; rate; warehouse; delivery date; workflow state | secondary technical and accounting details
Purchase Order | Procurement | Supplier; items; rates; delivery date; workflow state | less-used advanced sections
Stock Entry | Warehouse | Source warehouse; target warehouse; items; movement type; workflow state | non-operational details not needed in routine movement
Payment Entry | Finance | Party; payment type; amount; references; workflow state | secondary sections not needed for routine posting

## Implementation Sequence
Step | Action | Objective | Status
1 | Create first-wave workspaces | Establish simplified entry points for operational roles | Next
2 | Assign first-wave workspaces to role-slot users | Make daily navigation role-specific | Next
3 | Populate first-wave workspaces with shortcuts and reports | Deliver immediate usability gains | Next
4 | Validate with role-slot users | Check relevance, clutter, and missing links | Next
5 | Create second-wave workspaces | Complete management and support visibility | Later
6 | Reduce reliance on standard module workspaces | Shift users to role-based navigation | Later
7 | Refine form behavior by role | Further simplify high-volume documents | Later